## Sheet1
No. | Risk | Description | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Incomplete application deployed | Run issues or incomplete functionality | Medium | Critical | Developer | Revert to last working version (if exists) | Ensure testing is functioning and has appropriate line cover (>80%)
2 | Loss of work | Files not saved or power outage | Medium | High | Developer | Reproduce lost work | Push smaller, more frequent updates to GitHub to ensure minimal loss
3 | Unable to meet deadline | Poor scheduling or unforeseen circumstances | Low | High | Developer | Pursue possible extension to deadline | Ensure scheduling is realistic and leaves extra time for unexpected delays
4 | Developer inability to work | Illness or hardware failure | Low | Medium | Developer | Pursue possible extension if deadline cannot be met | Ensure hardware is maintained properly
5 | Data leak | Security bypassed and online files accessed by a third party | Low | High | GitHub | Inform customers about the data leak | Ensure passwords comply with safety standards
6 | Internet outage | ISP issues or maintenance | Medium | Low | ISP | Ensure work is saved locally | Ability to hotspot if internet is out for extended periods of time
7 | Poor optimisation | Application runs slowly due to inefficient code | Low | Low | Developer | Rework code to follow DRY, KISS and SOLID principles, etc. | Workflow should account for good coding principles from the start
8 | Virtual machine (VM) fails | Services delivered by a cloud-based computing provider runs into difficulty | Low | Critical | Cloud Service Provider | Run application on a back-up VM (if exists) | Ensure there is a back-up in case the main VM fails
9 | Cyber threats | Cloud-based platform is attacked | Low | High | Cloud Service Provider | Inform customers about the cyber attack and offer reimbursement | Ensure the service provider is in compliance with security standards